## Slide 1: ESA REGIONAL OFFICE
Result-Based Management Training
Session 1 – April 4 & 5th 2016

## Slide 2: Overall objective
For participants to be able to:
Apply RBM principles to the design and monitoring of programmes.
Use available RBM tools and approaches to strengthen results-oriented and equity focused programmes

## Slide 3: Agenda
DAY 1
DAY 2
Key Drivers and Principles of RBM
Problem Analysis
Application of Lenses
Outcome Chain
Prioritization
Strategies, Risks and Assumptions
Results Framework
Group Presentations
Implementation
Monitoring and Evaluation
Results Based Budgeting
Reporting

## Slide 4: KEY DRIVERS OF RBM & INTRODUCTION TO RBM PRINCIPLES
SESSION 1

## Slide 5: Session Objectives
Understand current drivers of RBM for UNICEF
Understand the RBM principles
Notes: Equity focus:
  Reaching the most deprived and vulnerable
  Differentiation with equality
MTSP:
  7 outcomes areas (education #4) with linkages / synergies
  Each SP outcome areas contributes on its own to reducing inequities + collectively, even greater result through synergies
  Each SP has its own ToC
  SP results framework has impact, outcome and output results, and each with indicator, baseline and target.
SDGs:
  Equitable results for all children, ‘leave no one behind’ Perhaps the most fundamental lesson of the MDGs was that, due to their focus on national averages and global aggregates, they failed to account for stagnating progress or – in some cases – growing inequalities among income and social groups and along gender lines.
Humanitarian Imperatives:
  As heard this morning, Shocks, including disasters and violent conflict are a threat to development
  Building resilient and sustainable societies means addressing existing and future risks in development planning and budgeting.
Reporting on results / transparency
  Accountability communication to the outside world on how and where UNICEF uses resources to leverage and achieve results for children.
  Enhance UNICEF’s visibility among key stakeholders
Funding and Donors:
  Improve UNICEF’s ability to leverage results and resources for children as donors are increasingly including transparency, and in particular IATI compliance as part of their assessment criteria of potential aid recipients.

## Slide 6: Starting the RBM conversation
Think about RBM in your work, then
Identify challenges you face in the application of RBM to your work
Use VIPP cards (2 cards/per response / participant)
Discuss commonalities and 3 retain cards for sharing
Individual and small group discussions
Notes: Equity focus:
  Reaching the most deprived and vulnerable
  Differentiation with equality
MTSP:
  7 outcomes areas (education #4) with linkages / synergies
  Each SP outcome areas contributes on its own to reducing inequities + collectively, even greater result through synergies
  Each SP has its own ToC
  SP results framework has impact, outcome and output results, and each with indicator, baseline and target.
SDGs:
  Equitable results for all children, ‘leave no one behind’ Perhaps the most fundamental lesson of the MDGs was that, due to their focus on national averages and global aggregates, they failed to account for stagnating progress or – in some cases – growing inequalities among income and social groups and along gender lines.
Humanitarian Imperatives:
  As heard this morning, Shocks, including disasters and violent conflict are a threat to development
  Building resilient and sustainable societies means addressing existing and future risks in development planning and budgeting.
Reporting on results / transparency
  Accountability communication to the outside world on how and where UNICEF uses resources to leverage and achieve results for children.
  Enhance UNICEF’s visibility among key stakeholders
Funding and Donors:
  Improve UNICEF’s ability to leverage results and resources for children as donors are increasingly including transparency, and in particular IATI compliance as part of their assessment criteria of potential aid recipients.

## Slide 7: Results-Based Management Cycle involves
RBM Conversations
Quality of analysis
Strategic priorities
Plausibility of delivering results
Ability to demonstrate results
Contributes to
Context and situation analysis
Strategic prioritization and planning
Implementation
Monitoring, Evaluation and Reporting
Learning and adjustment

## Slide 8: Key Drivers of Results-Based Management in UNICEF
The factors that
drive and shape
the application of RBM
in UNICEF include:
The equity focus
UNICEF’s Strategic Plan
SDGs and other global imperatives
Humanitarian imperatives
Funding and Donors
Reporting on results and transparency
Notes: Equity focus:
  Reaching the most deprived and vulnerable
  Differentiation with equality
MTSP:
  7 outcomes areas (education #4) with linkages / synergies
  Each SP outcome areas contributes on its own to reducing inequities + collectively, even greater result through synergies
  Each SP has its own ToC
  SP results framework has impact, outcome and output results, and each with indicator, baseline and target.
SDGs:
  Equitable results for all children, ‘leave no one behind’ Perhaps the most fundamental lesson of the MDGs was that, due to their focus on national averages and global aggregates, they failed to account for stagnating progress or – in some cases – growing inequalities among income and social groups and along gender lines.
Humanitarian Imperatives:
  As heard this morning, Shocks, including disasters and violent conflict are a threat to development
  Building resilient and sustainable societies means addressing existing and future risks in development planning and budgeting.
Reporting on results / transparency
  Accountability communication to the outside world on how and where UNICEF uses resources to leverage and achieve results for children.
  Enhance UNICEF’s visibility among key stakeholders
Funding and Donors:
  Improve UNICEF’s ability to leverage results and resources for children as donors are increasingly including transparency, and in particular IATI compliance as part of their assessment criteria of potential aid recipients.

## Slide 9: State of RBM
RBM issues account for 34% of all CO audit recommendations
34%
OVERALL
Notes: Equity focus:
  Reaching the most deprived and vulnerable
  Differentiation with equality
MTSP:
  7 outcomes areas (education #4) with linkages / synergies
  Each SP outcome areas contributes on its own to reducing inequities + collectively, even greater result through synergies
  Each SP has its own ToC
  SP results framework has impact, outcome and output results, and each with indicator, baseline and target.
SDGs:
  Equitable results for all children, ‘leave no one behind’ Perhaps the most fundamental lesson of the MDGs was that, due to their focus on national averages and global aggregates, they failed to account for stagnating progress or – in some cases – growing inequalities among income and social groups and along gender lines.
Humanitarian Imperatives:
  As heard this morning, Shocks, including disasters and violent conflict are a threat to development
  Building resilient and sustainable societies means addressing existing and future risks in development planning and budgeting.
Reporting on results / transparency
  Accountability communication to the outside world on how and where UNICEF uses resources to leverage and achieve results for children.
  Enhance UNICEF’s visibility among key stakeholders
Funding and Donors:
  Improve UNICEF’s ability to leverage results and resources for children as donors are increasingly including transparency, and in particular IATI compliance as part of their assessment criteria of potential aid recipients.

## Slide 10: QCPR resolution strong on RBM
Requests to accelerate work to develop and sustain a results culture at all levels within the funds and programmes…..and to invest in developing capacities and competencies for results-based management;
Implement a more robust, coherent and harmonized approach focused on results, which would streamline and improve the planning, monitoring, measurement and reporting on system-wide results at all levels,….
Demonstrate complete results chains that establish expected results at the output, outcome and impact levels and include measurable indicators with baselines, milestones and targets for monitoring…
………requests the United Nations development system to ensure increased mutual accountability for results-based management and reporting at the country level;
Notes: Equity focus:
  Reaching the most deprived and vulnerable
  Differentiation with equality
MTSP:
  7 outcomes areas (education #4) with linkages / synergies
  Each SP outcome areas contributes on its own to reducing inequities + collectively, even greater result through synergies
  Each SP has its own ToC
  SP results framework has impact, outcome and output results, and each with indicator, baseline and target.
SDGs:
  Equitable results for all children, ‘leave no one behind’ Perhaps the most fundamental lesson of the MDGs was that, due to their focus on national averages and global aggregates, they failed to account for stagnating progress or – in some cases – growing inequalities among income and social groups and along gender lines.
Humanitarian Imperatives:
  As heard this morning, Shocks, including disasters and violent conflict are a threat to development
  Building resilient and sustainable societies means addressing existing and future risks in development planning and budgeting.
Reporting on results / transparency
  Accountability communication to the outside world on how and where UNICEF uses resources to leverage and achieve results for children.
  Enhance UNICEF’s visibility among key stakeholders
Funding and Donors:
  Improve UNICEF’s ability to leverage results and resources for children as donors are increasingly including transparency, and in particular IATI compliance as part of their assessment criteria of potential aid recipients.

## Slide 11: Application of RBM in UNICEF
A shared understanding and commitment to results-based management approaches is an important prerequisite for success and delivery of results for women and children
Individual
Tasks
Competencies
Performance
Programme
Strategies
Outcomes
Performance
Country Office
Practices
Processes
Performance
Organisation
Systems
Value-proposition
Performance
RBM
Culture
Values
Country, RO. HQ Division
Programme/Section
Individual
Organization
Notes: RBM has often focused on the R of the approach.
The M : Management in RBM is the key: The active pursuit of desired results, monitoring performance, and adjusting actions as needed to continually strengthen achievement of results is essential.
As a management framework RBM:
provides a coherent framework.
emphasizes results throughout the planning, implementation, monitoring, reporting and learning stages of management.
ensures that processes, products and services achieve desired results.
ensures that interventions reflect the needs, priorities and visions of stakeholders.
RBM applies from the individual all the way to organisational performance and dependencies across the entire system. A culture shift on RBM needs to be felt across the entire spectrum. The commitment to results must be in evidence across all levels.
Focus is on a holistic application of RBM, from individual performance, all the way to how that impacts organisation performance. How do we ensure that RBM permeates the entire organisation
Individual level
With a focus on management, RBM should drive individual performance through a consideration of tasks and the competencies needed to accomplish them and ensure that contribution is being made to broader section and office goals. At this level a focus on roles and responsibilities is critical, necessary for meeting accountabilities in managing for results.
Programme or Section level
Performance should be measured in terms of how business is conducted, considering how the appropriate mix of strategies is leading to the achievement of outcomes. At the section level, RBM implies making sure that focus remains on the most efficient and effective means of achieving section objectives. The emphasis is on how processes, people and partners are managed to meet programme and section objectives.
Country office level
The offices adoption and ownership of RBM will be in evidence through its performance as measured using management indicators, giving an idea of how well practices and processes reflect RBM principles and concepts.
Organisation level
RBM in support of organisational performance must be in evidence in the systems and constantly used to articulate the organisations value-proposition.

## Slide 12: Any Questions?
Notes: Equity focus:
  Reaching the most deprived and vulnerable
  Differentiation with equality
MTSP:
  7 outcomes areas (education #4) with linkages / synergies
  Each SP outcome areas contributes on its own to reducing inequities + collectively, even greater result through synergies
  Each SP has its own ToC
  SP results framework has impact, outcome and output results, and each with indicator, baseline and target.
SDGs:
  Equitable results for all children, ‘leave no one behind’ Perhaps the most fundamental lesson of the MDGs was that, due to their focus on national averages and global aggregates, they failed to account for stagnating progress or – in some cases – growing inequalities among income and social groups and along gender lines.
Humanitarian Imperatives:
  As heard this morning, Shocks, including disasters and violent conflict are a threat to development
  Building resilient and sustainable societies means addressing existing and future risks in development planning and budgeting.
Reporting on results / transparency
  Accountability communication to the outside world on how and where UNICEF uses resources to leverage and achieve results for children.
  Enhance UNICEF’s visibility among key stakeholders
Funding and Donors:
  Improve UNICEF’s ability to leverage results and resources for children as donors are increasingly including transparency, and in particular IATI compliance as part of their assessment criteria of potential aid recipients.

## Slide 13: PROBLEM IDENTIFICATION & CAUSAL ANALYSIS
SESSION 2

## Slide 14: Session Objectives
Identify a problem / deprivation
Undertake causal analysis using the why’s and applying the 5 lenses
Notes: Equity focus:
  Reaching the most deprived and vulnerable
  Differentiation with equality
MTSP:
  7 outcomes areas (education #4) with linkages / synergies
  Each SP outcome areas contributes on its own to reducing inequities + collectively, even greater result through synergies
  Each SP has its own ToC
  SP results framework has impact, outcome and output results, and each with indicator, baseline and target.
SDGs:
  Equitable results for all children, ‘leave no one behind’ Perhaps the most fundamental lesson of the MDGs was that, due to their focus on national averages and global aggregates, they failed to account for stagnating progress or – in some cases – growing inequalities among income and social groups and along gender lines.
Humanitarian Imperatives:
  As heard this morning, Shocks, including disasters and violent conflict are a threat to development
  Building resilient and sustainable societies means addressing existing and future risks in development planning and budgeting.
Reporting on results / transparency
  Accountability communication to the outside world on how and where UNICEF uses resources to leverage and achieve results for children.
  Enhance UNICEF’s visibility among key stakeholders
Funding and Donors:
  Improve UNICEF’s ability to leverage results and resources for children as donors are increasingly including transparency, and in particular IATI compliance as part of their assessment criteria of potential aid recipients.

## Slide 15: Problem Analysis
Is the foundation
for a solid
Programme design
Good understanding of context
Clear problem identification and trend analysis,
Sound problem analysis, and
Appreciation of UNICEF comparative advantage and value proposition/addition
Will facilitate the
realization and
achievement of results
&

## Slide 16: Causal analysis– using the “whys”
WHY?
BECAUSE
WHY?
BECAUSE
WHY?
BECAUSE
Negative outcome, a right not respected, protected or fulfilled
KEY DEPRIVATION
Near and direct cause, most obvious link
IMMEDIATE CAUSES
Social organization, policies, inequitable distribution of resources, governance, political issues, culture
STRUCTURAL CAUSES
Shortfalls in social services, lack of access, harmful beliefs, practices
UNDERLYING CAUSES
LENSES
Notes: Causality enables us to analyse and explore who is most affected by a problem, how widespread the problem is and why that is happening.
A causal analysis allows for different streams of a problem to be examined in-depth. Causes are not linear, but are often a complex interaction of multiple streams that reinforce each other. More immediate causes are often easier to address, while more structural causes are more difficult and often longer-term, but tend to provide more sustainable solutions and results.

## Slide 17: Problem tree
STATE
BEHAVIOUR OF CHILD / DUTY BEARER
SYSTEMS
CONTEXT
Families subject their children to FGMC
FGMC practitioners are known and available in the community
Social and financial cost of FGMC is low
Lack of awareness of health and human rights consequences of FGMC
Community values FGMC and links to marriageability
FGM Practice is passed from generation to generation
Lack of enforcement of laws against FGMC
High prevalence of FGMC among children less than 15 years
FGMC is a social norm

## Slide 18: Group Work
Read the assigned case study
Identify one deprivation / inequity / risk and trends
Undertake a causal analysis
Develop a problem tree for that deprivation using the why’s methodology
  Use
  VIPP cards
  to construct the
  problem tree

## Slide 19: Any Questions?
Notes: Equity focus:
  Reaching the most deprived and vulnerable
  Differentiation with equality
MTSP:
  7 outcomes areas (education #4) with linkages / synergies
  Each SP outcome areas contributes on its own to reducing inequities + collectively, even greater result through synergies
  Each SP has its own ToC
  SP results framework has impact, outcome and output results, and each with indicator, baseline and target.
SDGs:
  Equitable results for all children, ‘leave no one behind’ Perhaps the most fundamental lesson of the MDGs was that, due to their focus on national averages and global aggregates, they failed to account for stagnating progress or – in some cases – growing inequalities among income and social groups and along gender lines.
Humanitarian Imperatives:
  As heard this morning, Shocks, including disasters and violent conflict are a threat to development
  Building resilient and sustainable societies means addressing existing and future risks in development planning and budgeting.
Reporting on results / transparency
  Accountability communication to the outside world on how and where UNICEF uses resources to leverage and achieve results for children.
  Enhance UNICEF’s visibility among key stakeholders
Funding and Donors:
  Improve UNICEF’s ability to leverage results and resources for children as donors are increasingly including transparency, and in particular IATI compliance as part of their assessment criteria of potential aid recipients.

## Slide 20: APPLICATION OF LENSES
SESSION 3

## Slide 21: Causal analysis– “whys” and “lenses”
WHY?
BECAUSE
WHY?
BECAUSE
WHY?
BECAUSE
Negative outcome, a right not respected, protected or fulfilled
KEY DEPRIVATION
Near and direct cause, most obvious link
IMMEDIATE CAUSES
Social organization, policies, inequitable distribution of resources, governance, political issues, culture
STRUCTURAL CAUSES
Shortfalls in social services, lack of access, harmful beliefs, practices
UNDERLYING CAUSES
Human rights
Equity
Gender
Determinants
Risk /
emergencies
LENSES
DO WE HAVE
EVIDENCE?
Notes: Causality enables us to analyse and explore who is most affected by a problem, how widespread the problem is and why that is happening.
A causal analysis allows for different streams of a problem to be examined in-depth. Causes are not linear, but are often a complex interaction of multiple streams that reinforce each other. More immediate causes are often easier to address, while more structural causes are more difficult and often longer-term, but tend to provide more sustainable solutions and results.

## Slide 22: Causal analysis– “whys” and “lenses”
Human rights
Equity
Gender
Determinants
Risk /
emergencies
Is the problem identified related to a deprivation of rights of children and women?
Does it highlight inequalities based on: geography, sex, income levels and population groups, etc.
Has a gender analysis been undertaken?
Have bottlenecks been analyzed against the 10 determinants?
Have risks and emergencies been considered?
Notes: Causality enables us to analyse and explore who is most affected by a problem, how widespread the problem is and why that is happening.
A causal analysis allows for different streams of a problem to be examined in-depth. Causes are not linear, but are often a complex interaction of multiple streams that reinforce each other. More immediate causes are often easier to address, while more structural causes are more difficult and often longer-term, but tend to provide more sustainable solutions and results.

## Slide 23: Group Work
Apply the 5 lenses to improve the problem identification and causal analysis
Identify strengths & weaknesses in problem analysis in the strategy note
  Use
  VIPP cards
  to construct the
  problem tree

## Slide 24: Any Questions?
Notes: Equity focus:
  Reaching the most deprived and vulnerable
  Differentiation with equality
MTSP:
  7 outcomes areas (education #4) with linkages / synergies
  Each SP outcome areas contributes on its own to reducing inequities + collectively, even greater result through synergies
  Each SP has its own ToC
  SP results framework has impact, outcome and output results, and each with indicator, baseline and target.
SDGs:
  Equitable results for all children, ‘leave no one behind’ Perhaps the most fundamental lesson of the MDGs was that, due to their focus on national averages and global aggregates, they failed to account for stagnating progress or – in some cases – growing inequalities among income and social groups and along gender lines.
Humanitarian Imperatives:
  As heard this morning, Shocks, including disasters and violent conflict are a threat to development
  Building resilient and sustainable societies means addressing existing and future risks in development planning and budgeting.
Reporting on results / transparency
  Accountability communication to the outside world on how and where UNICEF uses resources to leverage and achieve results for children.
  Enhance UNICEF’s visibility among key stakeholders
Funding and Donors:
  Improve UNICEF’s ability to leverage results and resources for children as donors are increasingly including transparency, and in particular IATI compliance as part of their assessment criteria of potential aid recipients.

## Slide 25: THEORY OF CHANGE: THE OUTCOME CHAIN
SESSION 4

## Slide 26: Session objectives
Be able to move from a problem tree to an outcome chain

## Slide 27: Theory of Change 1
By
Three
Conditions
If a problem is caused
Must
Be
Addressed
All three conditions
a
a
a
Interventions must not only be necessary, but also sufficient to achieve the expected result
Notes: If a problem is caused by three conditions, addressing only one or two conditions will not ensure that the problem will be solved.
For many years, UNICEF invested in training TBAs (traditional birth attendant), however without any significant reduction in maternal deaths or child death during birth.
Why?
Because the lack of knowledge or skills was just one factor that contributed to maternal death. Any obstetric emergency needs to be dealt with by a doctor in a sufficiently equipped health facility. Therefore, without rapid access to those facilities and without skilled doctors being available, the training of TBAs did little to reduce MMR.
Most programmes meant to increase girls enrolment and completion over the last dozens of years worked only with the Ministry of Education, trying to improve the school system. The programmes did not consider, for instance, the value that families and communities attach to girls education (i.e. very little value), or the lack of job opportunities for educated girls. If more girls were to complete education, these other issues need to be addressed as well.

## Slide 28: Solution tree/Outcome chain
Families do not subject their children to FGMC
Practice of FGM is interrupted
Laws against FGMC is enforced
Prevalence of FGMC among children less than 15 years is reduced
FGMC is no longer a social norm
FGMC practitioners are not available in the community
Social and financial cost of FGMC is high
Families understand the health and human rights consequences of FGMC
Community rejects FGMC and sanctions families that undertake FGM
Families subject their children to FGMC
High prevalence of FGMC among children less than 15 years
FGMC practitioners are known and available in the community
Social and financial cost of FGMC is low
Lack of awareness of health and human rights consequences of FGMC
Community values FGMC and links to marriageability
FGM Practice is passed from generation to generation
Lack of enforcement of laws against FGMC
FGMC is a social norm
Problem Tree

## Slide 29: What is a Theory of Change?
How will you use your programme to bring about change?
  The “What” and the “How” and the assumptions/risks
What will the change/success look like?
  What are the attributes and what are the criteria for success.
What is the pathway for change?
  Tipping point
How will you communicate it and report it?
  Visual plus narrative
Physical
Process
Psychological
Process
Economic
Process
Social
Process
CHANGE

## Slide 30: Group work
Convert the problem tree to an outcome chain/solution tree
  Present the
  outcome chain
  using
  VIPP cards
Present your justification for prioritization on a flipchart paper

## Slide 31: Any Questions?
Notes: Equity focus:
  Reaching the most deprived and vulnerable
  Differentiation with equality
MTSP:
  7 outcomes areas (education #4) with linkages / synergies
  Each SP outcome areas contributes on its own to reducing inequities + collectively, even greater result through synergies
  Each SP has its own ToC
  SP results framework has impact, outcome and output results, and each with indicator, baseline and target.
SDGs:
  Equitable results for all children, ‘leave no one behind’ Perhaps the most fundamental lesson of the MDGs was that, due to their focus on national averages and global aggregates, they failed to account for stagnating progress or – in some cases – growing inequalities among income and social groups and along gender lines.
Humanitarian Imperatives:
  As heard this morning, Shocks, including disasters and violent conflict are a threat to development
  Building resilient and sustainable societies means addressing existing and future risks in development planning and budgeting.
Reporting on results / transparency
  Accountability communication to the outside world on how and where UNICEF uses resources to leverage and achieve results for children.
  Enhance UNICEF’s visibility among key stakeholders
Funding and Donors:
  Improve UNICEF’s ability to leverage results and resources for children as donors are increasingly including transparency, and in particular IATI compliance as part of their assessment criteria of potential aid recipients.

## Slide 32: THEORY OF CHANGE: PRIORITIZATION
SESSION 5

## Slide 33: Session objectives
Understand how prioritization support results-focused programme design
Understand UNICEF’s comparative advantage
Be able to prioritize actions using the ‘funnel’ approach

## Slide 34
Prioritization: Scope and focus of programmes
FOCUS
SCOPE
OUT-OF-SCOPE
Which aspects of the problem, its causes and consequences will UNICEF focus on directly and primarily
“Everything” is lack focus
Interventions and investments
Which aspects are important and within reach and capacity of UNICEF to influence but beyond the focus of the programme?
Advocacy and programme monitoring
Which aspects are beyond the focus and scope of the programme?
Situation monitoring

## Slide 35: Prioritization
Comparative advantage
PRIORITIZATION
=
Criticality of the problem
Potential to make and demonstrate results / impact
+
+
Notes: If a problem is caused by three conditions, addressing only one or two conditions will not ensure that the problem will be solved.
For many years, UNICEF invested in training TBAs (traditional birth attendant), however without any significant reduction in maternal deaths or child death during birth.
Why?
Because the lack of knowledge or skills was just one factor that contributed to maternal death. Any obstetric emergency needs to be dealt with by a doctor in a sufficiently equipped health facility. Therefore, without rapid access to those facilities and without skilled doctors being available, the training of TBAs did little to reduce MMR.
Most programmes meant to increase girls enrolment and completion over the last dozens of years worked only with the Ministry of Education, trying to improve the school system. The programmes did not consider, for instance, the value that families and communities attach to girls education (i.e. very little value), or the lack of job opportunities for educated girls. If more girls were to complete education, these other issues need to be addressed as well.

## Slide 36: Comparative Advantage Analysis
What is our comparative advantage?
There must be capacity – staff, resources, expertise and an established track record of success, but these in themselves are not sufficient.
UNICEF must be seen, objectively, as being able to act better than any other development actor in the country on a specific issue.
MANDATE TO ACT
CAPACITY TO ACT
POSITIONING TO ACT BETTER THAN OTHERS
Notes: If a problem is caused by three conditions, addressing only one or two conditions will not ensure that the problem will be solved.
For many years, UNICEF invested in training TBAs (traditional birth attendant), however without any significant reduction in maternal deaths or child death during birth.
Why?
Because the lack of knowledge or skills was just one factor that contributed to maternal death. Any obstetric emergency needs to be dealt with by a doctor in a sufficiently equipped health facility. Therefore, without rapid access to those facilities and without skilled doctors being available, the training of TBAs did little to reduce MMR.
Most programmes meant to increase girls enrolment and completion over the last dozens of years worked only with the Ministry of Education, trying to improve the school system. The programmes did not consider, for instance, the value that families and communities attach to girls education (i.e. very little value), or the lack of job opportunities for educated girls. If more girls were to complete education, these other issues need to be addressed as well.

## Slide 37: Prioritization
UNICEF cannot address all deprivations, it needs to prioritize based on its comparative advantages using 5 key filters:
Criticality of national challenges / inequities
Mandate: Strategic Plan, alignment with global / sectoral priorities
Position to act better than other partners
Capacities and resources (human, financial, knowledge, technology, partners)
Lessons learned, knowledge of what works and what does not
Priority issues to be addressed by UNICEF
SHARPENING FOCUS
Notes: UNICEF cannot address all deprivations. It has to focus its interventions on a few priority areas
Central to prioritization is the notion of UNICEF’s comparative advantage having the mandate, resources and capacity to act effectively
Five key filters can support prioritization and selection of programme areas that UNICEF should address in a CPD
A “prioritization funnel” helps guide consideration of the mutually reinforcing criteria or filters to choose and select projects and programmes, including their strategies.

## Slide 38: Comparative Advantage: Stakeholder Mapping
Stakeholder Mapping Tool
List the key stakeholders involved in this challenge /problem area
What is each stakeholder already doing / likely to be doing in this area?
Identify the Unique Niche of UNICEF
    UNICEF is the only agency that can act in this area in this way
    UNICEF has a unique contribution to make in this area
    UNICEF is better positioned than other actors
Exercise
Notes: If a problem is caused by three conditions, addressing only one or two conditions will not ensure that the problem will be solved.
For many years, UNICEF invested in training TBAs (traditional birth attendant), however without any significant reduction in maternal deaths or child death during birth.
Why?
Because the lack of knowledge or skills was just one factor that contributed to maternal death. Any obstetric emergency needs to be dealt with by a doctor in a sufficiently equipped health facility. Therefore, without rapid access to those facilities and without skilled doctors being available, the training of TBAs did little to reduce MMR.
Most programmes meant to increase girls enrolment and completion over the last dozens of years worked only with the Ministry of Education, trying to improve the school system. The programmes did not consider, for instance, the value that families and communities attach to girls education (i.e. very little value), or the lack of job opportunities for educated girls. If more girls were to complete education, these other issues need to be addressed as well.

## Slide 39: Group work
Undertake a stakeholder mapping against the outcome chain
Using the ‘funnel’ approach select the deprivation / inequity that
  UNICEF will focus on directly and primarily – in focus
  UNICEF will influence – in scope (identify partners)
  Are out scope of UNICEF’s programme
  Present the
  outcome chain
  using
  VIPP cards
Present your justification for prioritization on a flipchart paper

## Slide 40: Any Questions?
Notes: Equity focus:
  Reaching the most deprived and vulnerable
  Differentiation with equality
MTSP:
  7 outcomes areas (education #4) with linkages / synergies
  Each SP outcome areas contributes on its own to reducing inequities + collectively, even greater result through synergies
  Each SP has its own ToC
  SP results framework has impact, outcome and output results, and each with indicator, baseline and target.
SDGs:
  Equitable results for all children, ‘leave no one behind’ Perhaps the most fundamental lesson of the MDGs was that, due to their focus on national averages and global aggregates, they failed to account for stagnating progress or – in some cases – growing inequalities among income and social groups and along gender lines.
Humanitarian Imperatives:
  As heard this morning, Shocks, including disasters and violent conflict are a threat to development
  Building resilient and sustainable societies means addressing existing and future risks in development planning and budgeting.
Reporting on results / transparency
  Accountability communication to the outside world on how and where UNICEF uses resources to leverage and achieve results for children.
  Enhance UNICEF’s visibility among key stakeholders
Funding and Donors:
  Improve UNICEF’s ability to leverage results and resources for children as donors are increasingly including transparency, and in particular IATI compliance as part of their assessment criteria of potential aid recipients.

## Slide 41: THEORY OF CHANGE: STRATEGIES, RISKS AND ASSUMPTIONS
SESSION 6

## Slide 42: Session objectives
Define programme and implementation strategies
Identify key assumptions and risks
Assess the risk level
Mitigate risks

## Slide 43
Managing for results
What will UNICEF do = Programme Strategies + Implementation Strategies
Programme Strategies
Protect
Promote
Prevent
Care
Programme
Interventions
Systems (MORES)
Interventions
Evidence
Generation,
policy dialogue
and advocacy
Partnerships
C4D
Identification
and promotion
of innovation
South-south
and triangular
cooperation
Support to
integration
and
cross-sectoral
linkages
Service delivery
Capacity
Building
Enabling Environment
Supply
Demand
Quality
Social Norms
Legislation / Policy
Budget / Expenditure
Management / Coordination
Availability of Essential Commodities / inputs
Access to Adequately Staffed Services, Facilities, and Information
Quality
Financial Access
Social & Cultural Practices / Beliefs
Timing & Continuity of Use

## Slide 44
Assumptions about factors that affect outcomes
Assumptions
Programme factors
Within control of the programme
Risks
Non programme factors
Beyond control of the programme but with significant impact on results
    Partners’ contributions
    Programme resources
    Programme implementation/delivery
    Governance and Programme management: Managing for results
    Operating environment: Demographics, industry climate, political climate, economic climate, conflict, emergency, etc.
    Generate opportunities to be exploited and risks that should be known, monitored, managed and mitigated
FACTORS
FACTORS

## Slide 45
Risk Assessment and Mitigation Strategies
Risks are assessed along 2 dimensions
Leading to overall risk level
Lijellihood
Impact
High
Medium
Low
Likelihood
"What is the likelihood of the risk
materializing given our existing controls?"
Minimal
Critical
Impact
"What is the impact of the risk materializing
on the grant's objectives & impact?"
Mild
Severe

## Slide 46
Group Work
Identify the programme interventions and implementation strategies that will support actions to bring about change and deliver results
List key assumptions
Identify and assess, and develop mitigation strategies for 2 to 3 risks
Include 1 and 2 in the outcome chain using different color VIPP cards

## Slide 47: Any Questions?
Notes: Equity focus:
  Reaching the most deprived and vulnerable
  Differentiation with equality
MTSP:
  7 outcomes areas (education #4) with linkages / synergies
  Each SP outcome areas contributes on its own to reducing inequities + collectively, even greater result through synergies
  Each SP has its own ToC
  SP results framework has impact, outcome and output results, and each with indicator, baseline and target.
SDGs:
  Equitable results for all children, ‘leave no one behind’ Perhaps the most fundamental lesson of the MDGs was that, due to their focus on national averages and global aggregates, they failed to account for stagnating progress or – in some cases – growing inequalities among income and social groups and along gender lines.
Humanitarian Imperatives:
  As heard this morning, Shocks, including disasters and violent conflict are a threat to development
  Building resilient and sustainable societies means addressing existing and future risks in development planning and budgeting.
Reporting on results / transparency
  Accountability communication to the outside world on how and where UNICEF uses resources to leverage and achieve results for children.
  Enhance UNICEF’s visibility among key stakeholders
Funding and Donors:
  Improve UNICEF’s ability to leverage results and resources for children as donors are increasingly including transparency, and in particular IATI compliance as part of their assessment criteria of potential aid recipients.

## Slide 48: Agenda
DAY 1
DAY 2
Key Drivers and Principles of RBM
Problem Analysis
Application of Lenses
Outcome Chain
Prioritization
Strategies, Risks and Assumptions
Results Framework
Group Presentations
Implementation
Monitoring and Evaluation
Results Based Budgeting
Reporting

## Slide 49: THE RESULTS FRAMEWORK
SESSION 7

## Slide 50: Session objectives
Draw linkages between the results chain and the Theory of Change
Understand the differences in the level of results and how to formulate results statements
Understand how to incorporate a Measurement Framework

## Slide 51: What is a result
A result is a measurable or describable change arising
from a cause and effect relationship for which you want to be held accountable
A subject of change
A dimension of change
A qualifier of change
A RESULTS MUST HAVE
Notes: Example:
Number of children registered increased by 25% by 2019

## Slide 52: 6 principles for formulating results
Clarity on the level (output, outcome or impact) and accountabilities
SMARTer results, supplemented by SMART indicators
Coherent results chains, applying the if-then logic otherwise asking the question – so what between levels
Uses change language, that places emphasis on the subject of change
Considers equity, human rights, gender, determinants and risks
Clear relationship with issues identified in the SitAn
Notes: Outcomes and Impact entail shared accountability
Supports the achievement of national priorities or results
Notable pitfall: Result statement not combined with strategy
SMART should not be used as a straight jacket – considerable judgement needs to be used in formulating good results statements. At the end of the day, the vertical logic and knowledge of how others are contributing along the results chain will determine to a large extent its strength.

## Slide 53: Hierarchy of Results
Long term changes in the rights / deprivation / inequities in situation of children and women
Nationally owned
IMPACT
Changes in behavior or performance of targeted institutions or individuals manifesting in coverage and equity of services / interventions
UNICEF contributes to these changes
OUTCOME
Changes in capacities of individuals or institutions including new products, skills, abilities and services
Attributable to programme funds and management – therefore high degree of accountability
OUTPUT
Notes: As results-based management is about change, worth being precise about for whom and where this change occurs. In human rights language – being specific about the subject of change (duty bearers or rights holders).

## Slide 54
IMPACT
OUTCOME
OUTPUT
Improved Literacy
Increased Enrolment
Increased access to quality schools
Hierarchy of Results - Example

## Slide 55: Results Chain
Result
Result
Result
Result
Result
Result
Result
Result
Result
Activities
Inputs
Activities
Inputs
Activities
Inputs
Activities
Inputs
Activities
Inputs
IF
THEN
IF
THEN
IF
THEN
Result
IF
THEN
Risks and Assumptions
Risks and Assumptions
Risks and Assumptions
Risks and Assumptions
Notes: Following up from the development of the ToC
Developing a chain of results is an iterative process of checking the “if, then” logic, reviewing and improving on the results statements at the various levels of the results chain. Each level in the chain of results should include all the results that are both sufficient and necessary to achieve the next level of results considering underlying assumptions, internal and external risks in the particular context. The way to determine if the necessary and sufficient results have been identified is to refer to evidence of what works. Such evidence is available in research and evaluation or from the experience of the stakeholders who are developing the chain of results. If there are gaps in the chain, they should be filled.
It is important to understand the “cause and effect”, “if, then”, reasoning behind the results-chain. The results chain includes an impact statement as a response to the manifestation of the development issue, challenge, problem. It shows that if such an impact (the fourth level of results) is to be achieved then certain previous results are needed, and if these third level results are to be attained, then another set of previous second level results are necessary. This type of reasoning is useful to uncover a continuum of results from the highest to the lowest order that are all required to achieve the desired impact.
The reverse logic can also be applied to verify whether a programme is on the right track i.e. if certain inputs are provided and activities implemented, will they lead to the expected results? Will the first level expected results together contribute to the second and third levels of expected results? Will all these results eventually have the desired impact?

## Slide 56: What is an indicator
Indicators are measures used to monitor progress made towards the achievement of intended results or the application of desired processes.
  Result statement: Within 3 years, 90% of girls enrolled in catch-up education courses are mainstreamed into primary schools
  Indicator: % of girls enrolled in catch-up education courses mainstreamed into primary schools
  Target Year 1: 45% of girls enrolled in catch-up education courses are mainstreamed into primary schools
  Performance of project in Year 1: 65% of girls enrolled in catch-up education courses are mainstreamed into primary schools
An indicator is neutral, does not pre-judge or set targets, is therefore “empty of data”, i.e., data still has to be collected
EXAMPLE

## Slide 57: Performance Indicators
…measure impacts, outcomes, outputs – due to the performance of a project or programme.
….compare results achieved with results expected or planned
….allow performance to be judged, evaluated
….allow programmes to be adjusted
Situation
Start of programme
End of programme
Results
Performance
indicators

## Slide 58: Quality Criteria for Indicators
Ratio of indicators to result
Level of indicators
Measurability of indicators
Quality of indicators
The indicators should be relevant to the result. The number of indicators per one result should be kept to a minimum, preferably 1 to 3, depending on the level of the result.
The indicators should measure the result directly or be an obvious proxy.
Indicators should be SMART with a clear unit of measurement and an operational output.
Baselines, targets and a reliable data source must be provided for the indicator.
HORIZONTAL LOGIC

## Slide 59: Measurement Framework for Results
Baselines and Targets
What are they?
Why are they important for measuring results?
What improvements can we make in using them?
Notes: Frequently referred to as the Monitoring and Evaluation Framework – is used to systematically plan the collection of relevant information for monitoring, learning and reporting. The framework helps track the achievement of results.

## Slide 60: Group work
Working from the ToC developed:
Review the Results Framework by discussing the attributes and success criteria
Make results SMARTer –
  Refine the outcome and related output statements
  Check the if-then-assumptions logic and refine
  Refine indicator for each of the results statements, and identify related means of verification and frequency for reporting.
  Capture the Baseline & Target (if not possible explain how you will go about it)
Remember to use all the criteria for the formulation of sound results and measurement
Groups shall capture their work on the flip-charts using the results framework template.

## Slide 61: Any Questions?
Notes: Equity focus:
  Reaching the most deprived and vulnerable
  Differentiation with equality
MTSP:
  7 outcomes areas (education #4) with linkages / synergies
  Each SP outcome areas contributes on its own to reducing inequities + collectively, even greater result through synergies
  Each SP has its own ToC
  SP results framework has impact, outcome and output results, and each with indicator, baseline and target.
SDGs:
  Equitable results for all children, ‘leave no one behind’ Perhaps the most fundamental lesson of the MDGs was that, due to their focus on national averages and global aggregates, they failed to account for stagnating progress or – in some cases – growing inequalities among income and social groups and along gender lines.
Humanitarian Imperatives:
  As heard this morning, Shocks, including disasters and violent conflict are a threat to development
  Building resilient and sustainable societies means addressing existing and future risks in development planning and budgeting.
Reporting on results / transparency
  Accountability communication to the outside world on how and where UNICEF uses resources to leverage and achieve results for children.
  Enhance UNICEF’s visibility among key stakeholders
Funding and Donors:
  Improve UNICEF’s ability to leverage results and resources for children as donors are increasingly including transparency, and in particular IATI compliance as part of their assessment criteria of potential aid recipients.

## Slide 62: PLENARY PRESENTATIONS
SESSION 8

## Slide 63: IMPLEMENTATION
SESSION 9

## Slide 64: Session Objectives
Identify risks to the delivery of results
Identification of implementation modalities
Moving from outputs to deliverables to activities – and scheduling
Resource allocation
Tips for good work planning

## Slide 65
Identification of Risks to Implementation and Delivery of Results
Risks are assessed along 2 dimensions
Leading to overall risk level
Lijellihood
Impact
High
Medium
Low
Likelihood
"What is the likelihood of the risk
materializing given our existing controls?"
Minimal
Critical
Impact
"What is the impact of the risk materializing
on the grant's objectives & impact?"
Mild
Severe
budget / cash management
Fraud / misuse of resources
Funding / External stakeholder relations
Governance / accountability
Human resources / unethical behavior
ICT systems / information security
Natural disasters / epidemics
Organizational strategy / neutrality
RBM and reporting
Safety and security
Supply and logistics
Other
Types of Risks

## Slide 66: Implementation Strategies
Select strategies to implement the results in the most effective and direct manner.
Selection of strategies should consider inter alia:
Organisational initiatives
Lessons learned from previous application of strategy
Capacity to execute strategy
Analysis of risks and assumptions
Economy, efficiency and effectiveness (or ‘value for money’)
Sustainability of results, with a focus on building capacity at national and sub-national levels for ‘development’ results
IMPLEMENTATION
STRATEGIES
Capacity Development
Evidence Based Advocacy
C4D
Service Delivery
Innovations
Partnerships
South South cooperation
Cross Sectoral integration
Managing for Results

## Slide 67: Implementation Modalities
UNICEF generally applies one or more of four implementation modalities to achieve a result:
Working with Government
Working with Civil Society Organizations
Working with Other UN Agencies
UNICEF Directly implementing an activity
Considering the most suitable modality takes into account the specific needs of an intervention and operating environment, and comparative advantage to support achievement of results
Economy – obtaining inputs of appropriate quality at the right price
Efficiency – timely allocation and use of resources to achieve outputs
Effectiveness – the most appropriate strategy and modality for achieving results

## Slide 68
Missing Link: Moving From Activities to Results
Key deliverables linked to the strategies:
  Products
  Services
  Capacities
Scheduling
Resourcing

## Slide 69: Resourcing
Cash
Supplies
People
Determining what resources - people (staff + external), cash, and supplies - are needed
When they will be needed to implement activities as outlined in workplans
In UNICEF, there are three primary types of inputs:

## Slide 70: Work planning considerations
Quality assurance
Involvement of counterparts and development partners
Review outputs and strategies as outlined in strategic plans (CPD)
Determine activities for corresponding strategies identified
Input requirements to carry out activities
Time required to carry out activities
Implementation modalities
Partners and responsible persons
Funding sources and gaps
Presentation in VISION

## Slide 71: Any Questions?
Notes: Equity focus:
  Reaching the most deprived and vulnerable
  Differentiation with equality
MTSP:
  7 outcomes areas (education #4) with linkages / synergies
  Each SP outcome areas contributes on its own to reducing inequities + collectively, even greater result through synergies
  Each SP has its own ToC
  SP results framework has impact, outcome and output results, and each with indicator, baseline and target.
SDGs:
  Equitable results for all children, ‘leave no one behind’ Perhaps the most fundamental lesson of the MDGs was that, due to their focus on national averages and global aggregates, they failed to account for stagnating progress or – in some cases – growing inequalities among income and social groups and along gender lines.
Humanitarian Imperatives:
  As heard this morning, Shocks, including disasters and violent conflict are a threat to development
  Building resilient and sustainable societies means addressing existing and future risks in development planning and budgeting.
Reporting on results / transparency
  Accountability communication to the outside world on how and where UNICEF uses resources to leverage and achieve results for children.
  Enhance UNICEF’s visibility among key stakeholders
Funding and Donors:
  Improve UNICEF’s ability to leverage results and resources for children as donors are increasingly including transparency, and in particular IATI compliance as part of their assessment criteria of potential aid recipients.

## Slide 72: MONITORING AND EVALUATION
SESSION 10

## Slide 73: Session Objectives
Understand the importance of planning for monitoring and evaluation
To explore ways of improving monitoring practice
Develop understanding of critical complementarities between monitoring and evaluation
Understand how evaluation supports results-based management

## Slide 74: Introduction
Monitoring begins from a well thought-out Measurement Plan that is linked to the Results Framework
Monitoring requires adequate attention to data collection methods, tools and protocols. The choice of these depends on the results being monitored, contextual, efficiency and other considerations.
Planning for monitoring is critical to guide the preparation of data collection for overall programme management.
It is important to anticipate how monitoring data will be used as it can be costly in both money and time. Collecting information that will not be used is inefficient.
Quality reporting is required to demonstrate UNICEF’s contribution to results

## Slide 75: Framework for programme monitoring
Programme monitoring
  is about good programming
  operates within an institutional and accountability framework’ voices not routinely captured
  Technology offers opportunity for improving programme monitoring
Data use
Real-time monitoring
End-user monitoring
Citizen engagement

## Slide 76: Level of Results and Programme Monitoring
Impact
Outcomes
Outputs
Activities
Inputs
Level 4 monitoring
Level 3 monitoring
Level 2 monitoring
Situation monitoring
Results monitoring
Programmatic Visits / Field Monitoring
Spot checks
Notes: There are a number of UNICEF/UN specific monitoring frameworks including MoRES and HACT.
Level 2 of MoRES is the same as Implementation monitoring. It looks at inputs, activities and outputs (although in MoRES this is analyzed from a bottleneck and barriers perspective). It is also the same as Programmatic Visits as defined in the HACT Framework
Level 3 of MoRES is these same as Results Monitoring. It looks at outputs and outcomes. In MoRES, the output level analysis is from the perspective of barriers and bottlenecks. For example, absence of a health clinic (result at output level) could be a bottleneck to achieving high level results at outcome level (E.g. delivery at health facility)

## Slide 77: Key Questions for Programme Monitoring
Are we implementing as planned ?
Implementation monitoring
Are we achieving results ?
Results monitoring
How is the situation of children or the wider context changing?
Situation monitoring
Key Questions
Monitoring
Focus
Inputs
Activities
Outputs
Outcomes
Impact
Programme monitoring
Situation monitoring
Notes: Implementation monitoring: continuous or periodic oversight of the implementation of an activity to establish the extent to which inputs, work schedules, other required actions and targeted processes are proceeding according to plan.
Results monitoring: A continuous process of data gathering, analysis to measure and report on results at periodic intervals, and utilizing the data in programme management and decision-making. Results monitoring provides information to assess progress in reduction of bottlenecks that impede achievement of results.
Situation Monitoring: Monitoring is the systematic tracking of a condition or set of conditions, such as the situation of children and women. Situation monitoring measures change or lack of change in a condition or a set of conditions. Monitoring the situation of children and women and development goals such as the Sustainable Development Goals (SDGs) is necessary when trying to draw conclusions about the impact of programmes or policies.

## Slide 78: What is an Evaluation?
An evaluation is an assessment, as systematic and impartial as possible, of a programme, strategy, policy, sector, operational area or institutional performance.

## Slide 79: Purpose of Evaluation
PROGRAMME RESULTS
Establish contributions made
Accountability
Learning
Accountability for results
Organizational learning and improvement
Contribute to knowledge generation
Evidence-based policy advocacy

## Slide 80: Evaluation Contributes to:
Standard Evaluation Criteria
Gender Equality & HRBAP Criteria
Humanitarian Response Evaluation Criteria
Relevance
Efficiency
Effectiveness
Impact
Sustainability
Equity, gender equality perspective and human rights-based approach incorporated in intervention design / implementation?
Coverage
Coordination
Coherence
Connectedness
Protection

## Slide 81: Managing Evaluations
Evaluations are selected strategically and prioritized during programme design, with an indication of resource allocation and how they will be conducted and managed (costed evaluation plans).
Integrated Monitoring and Evaluation Plans (IMEPs) capture synergies and bring coherence in these activities for the entire country programme
Evaluations are reflected in annual plans and that ensure the allocation of adequate human and financial resources
A quality assurance and clearance mechanism exists for the preparation, conduct and finalization of evaluations
Evaluation findings are sound and management response is established for key recommendations

## Slide 82: Any Questions?
Notes: Equity focus:
  Reaching the most deprived and vulnerable
  Differentiation with equality
MTSP:
  7 outcomes areas (education #4) with linkages / synergies
  Each SP outcome areas contributes on its own to reducing inequities + collectively, even greater result through synergies
  Each SP has its own ToC
  SP results framework has impact, outcome and output results, and each with indicator, baseline and target.
SDGs:
  Equitable results for all children, ‘leave no one behind’ Perhaps the most fundamental lesson of the MDGs was that, due to their focus on national averages and global aggregates, they failed to account for stagnating progress or – in some cases – growing inequalities among income and social groups and along gender lines.
Humanitarian Imperatives:
  As heard this morning, Shocks, including disasters and violent conflict are a threat to development
  Building resilient and sustainable societies means addressing existing and future risks in development planning and budgeting.
Reporting on results / transparency
  Accountability communication to the outside world on how and where UNICEF uses resources to leverage and achieve results for children.
  Enhance UNICEF’s visibility among key stakeholders
Funding and Donors:
  Improve UNICEF’s ability to leverage results and resources for children as donors are increasingly including transparency, and in particular IATI compliance as part of their assessment criteria of potential aid recipients.

## Slide 83: RESULTS BASED BUDGETING
SESSION 11

## Slide 84: Session Objectives
Understand the principles of RBB and how to apply them when planning for results

## Slide 85: Steps in Results Based Budgeting
CPD
Allocation [ROMP]
(at outcome level)
Identify outputs & indicators
Define Deliverables
Define Strategies
3
Define Activities
Define Implementation Modalities:
Government, NGO, other UN agencies Direct implementation
Identify Inputs:
Staff, Travel, Equipment, Consultants, Supplies, Operations
Cost inputs
Direct & indirect costs
Assess affordability against the resource envelope
Reprioritize:
Must do
Mobilize resources
Drop
Projected Resources envelope (RR, OR, IB)
4
5
1
2
6
7
8
9

## Slide 86: Types of Costs
STAFF COSTS
UNIT COST
QUANTITIES
PROGRAMME
COSTS
OPERATIONS
COSTS
COST OF STAFF
COST OF TRAVEL
COST OF CONSULTANCIES
COST OF SUPPLIES & EQUIPMENT
COST OF ACTIVITIES
COST OF RENT, IT SERVICES, VEHICLES, SECURITY, ETC.
TOTAL COST BY OUTPUT, OUTCOME, PROGRAMME COMPONENT
AND BY TYPE OF FUNDS

## Slide 87: Integrated Budget
TOTAL COST BY OUTPUT, OUTCOME, PROGRAMME COMPONENT
AND BY TYPE OF FUNDS
Integrated Budget
Institutional Budget
Programmes, including Global and Regional Programme
Programme Effectiveness
Management
UN Development Coordination
Special Purpose:
Capital Investments
Private Fundraising and Partnerships
Procurement Services
OR / RR

## Slide 88: Tips for Sound Budgeting Practices
Is the programme affordable? Do the budget lines look economic, plausible, reasonable and realistic?
Is the budget aligned with programme priorities?
Does the overall budget reflect the Theory of Change – particularly the programme areas, determinants and strategies? Do the budget lines correspond to the project design and to the planned results as indicated in the Results Framework? Keep PIDB coding in mind!
Where could the budget be cut without substantially hampering the desired results?
Does the budget attribution look reasonable over the planned period (planning per year)?
Which budget lines are direct costs (directly linked to the activities/progress) and which budget lines are indirect costs (independent of operational activities/progress)?
Last but not least, are the calculations of the budget lines and of the totals mathematically correct?
ESAR expenditures,
2014-2015

## Slide 89: Any Questions?
Notes: Equity focus:
  Reaching the most deprived and vulnerable
  Differentiation with equality
MTSP:
  7 outcomes areas (education #4) with linkages / synergies
  Each SP outcome areas contributes on its own to reducing inequities + collectively, even greater result through synergies
  Each SP has its own ToC
  SP results framework has impact, outcome and output results, and each with indicator, baseline and target.
SDGs:
  Equitable results for all children, ‘leave no one behind’ Perhaps the most fundamental lesson of the MDGs was that, due to their focus on national averages and global aggregates, they failed to account for stagnating progress or – in some cases – growing inequalities among income and social groups and along gender lines.
Humanitarian Imperatives:
  As heard this morning, Shocks, including disasters and violent conflict are a threat to development
  Building resilient and sustainable societies means addressing existing and future risks in development planning and budgeting.
Reporting on results / transparency
  Accountability communication to the outside world on how and where UNICEF uses resources to leverage and achieve results for children.
  Enhance UNICEF’s visibility among key stakeholders
Funding and Donors:
  Improve UNICEF’s ability to leverage results and resources for children as donors are increasingly including transparency, and in particular IATI compliance as part of their assessment criteria of potential aid recipients.

## Slide 90: REPORTING
SESSION 12

## Slide 91: Session Objectives
Identify elements for effective reporting on UNICEF’s contribution to results.
Understand the importance of quality reporting to meeting accountabilities, learning and how UNICEF is perceived.
Recognize the importance of transparency to reporting.

## Slide 92: Quality of Results Reporting in ESAR
OVERALL
Poor quality of reporting
Average quality of reporting
Good quality of reporting
Source: 2015 Country Office Annual Report review

## Slide 93: Why Do We Report?
REPORTS
Establish contributions made
Accountability
Learning

## Slide 94: Types of Reports
RAM
COAR / ROAR
DONOR REPORTS
SITREPS
ANNUAL UN RESULTS REPORTS

## Slide 95: Effective Reporting
A proper RBM report contains two main parts:
A Description of what results have been achieved, using the identified indicators, to demonstrate progress made.
A strong analysis of how these results were obtained, with whom, and the resources and conditions that contributed to their achievement.
The analysis should also provide and indication of shortfalls in the achievement of results, where needed and an explanation of any difficulties, failures, lessons learned as well as future direction.
.

## Slide 96: Effective reporting on Results
Describe all steps of the results-chain (inputs, activities, outputs and outcomes) to support your ToC and show the linkages between interventions and results
Be transparent and effectively analyse bottlenecks and opportunities and how the bottlenecks are being addressed
Acknowledge the contribution of partners to results
Show lessons learned and how knowledge gained from monitoring and evaluation of programmes is used to inform decision-making
Identify next steps: so what?
Assess all indicators and provide reliable data sources
Provide a results- focused account of achievements along the results chain

## Slide 97: 8 Tips to Improve Results-Based Reporting
Be clear and concise
Avoid jargon and the abusive use of acronyms
Adapt your language to the audience: Public donors (Govt and bilaterals); Natcoms / Private sector donors
Use the change language
Report on results, not processes
Contextualize progress achieved
Analyze progress
Be careful with results attribution; acknowledge the exact contribution of partners to results

## Slide 98: Establish Workflow Processes
In order to ensure quality donor reporting, the right work processes must be in place:
Do not begin reports 2 days before report is due. Time is needed for good quality.
Ensure clear workflow processes and accountabilities for reporting:
    Who monitors reporting obligations?
    Who ensures quality assurance of reports?
    Who clears the reports?
Does the office culture ensure that reporting is taken seriously?

## Slide 99: Any Questions?
Notes: Equity focus:
  Reaching the most deprived and vulnerable
  Differentiation with equality
MTSP:
  7 outcomes areas (education #4) with linkages / synergies
  Each SP outcome areas contributes on its own to reducing inequities + collectively, even greater result through synergies
  Each SP has its own ToC
  SP results framework has impact, outcome and output results, and each with indicator, baseline and target.
SDGs:
  Equitable results for all children, ‘leave no one behind’ Perhaps the most fundamental lesson of the MDGs was that, due to their focus on national averages and global aggregates, they failed to account for stagnating progress or – in some cases – growing inequalities among income and social groups and along gender lines.
Humanitarian Imperatives:
  As heard this morning, Shocks, including disasters and violent conflict are a threat to development
  Building resilient and sustainable societies means addressing existing and future risks in development planning and budgeting.
Reporting on results / transparency
  Accountability communication to the outside world on how and where UNICEF uses resources to leverage and achieve results for children.
  Enhance UNICEF’s visibility among key stakeholders
Funding and Donors:
  Improve UNICEF’s ability to leverage results and resources for children as donors are increasingly including transparency, and in particular IATI compliance as part of their assessment criteria of potential aid recipients.

## Slide 100: Wrap-up
DAY 1
DAY 2
Key Drivers and Principles of RBM
Problem Analysis
Application of Lenses
Outcome Chain
Prioritization
Strategies, Risks and Assumptions
Results Framework
Group Presentations
Implementation
Monitoring and Evaluation
Results Based Budgeting
Reporting

## Slide 101
Thank You!